## Sprint Plan
Day | Task | Status
Mon 31 Mar | Understand the Architecture of old GTL & HRMS, RnD on how we can merge Tables of GTL & HRMS. Plan strategies how to build things | Done
Tue 01 Apr | Create Unified system, GTL & HRMS, Migrate Data | Done
Wed 02 Apr | Role based dashboards, find loop holes and fix them | Done
Thu 03 Apr | Create Swagger, Org. charts, few minor tweaks, add responsiveness | Done
Fri 04 Apr | Review the whole system, every single page and functionality, Consistent theming | Planned
Mon 07 Apr | Data Seeding, verify roles and fix teams and reportings | Planned
Tue 08 Apr | Add visual charts on dashboard — attendance trends, hours by project, team performance graphs | Planned
Wed 09 Apr | Email alerts when leave is approved/rejected, when WFH is assigned, when attendance request is handled | Planned
Thu 10 Apr | Allow employees to upload profile photo or capture from webcam. Show photos in directory, org chart, CV | Planned
Fri 11 Apr | HR can upload Excel file to bulk-fill employee profiles (430 employees have empty profiles) | Planned
Mon 14 Apr | Auto-sync ZKTeco biometric devices every 5 minutes instead of manual sync. Auto-close missed checkouts at midnight | Planned
Tue 15 Apr | Test entire system on mobile phones and tablets — make sure everything works on small screens | Planned
Wed 16 Apr | Setup production server — install Nginx, SSL certificate, configure domain, database backups | Planned
Thu 17 Apr | Deploy application on production server alongside old PHP systems (zero downtime, both run together) | Planned
Fri 18 Apr | Full testing with real users — employee login, lead approval, admin management. Get sign-off for go-live | Planned